# Site Meeting Minutes, Week 18

Community library extension. Meeting no. 18, held in the site office.

| Attendee | Role |
| --- | --- |
| Project manager | Owner representative |
| Site manager | Main contractor |
| Architect | Design team |
| Services engineer | Design team |
| Structural engineer | Design team (items 3 and 4 only) |

# 1. Programme

The contractor reported the project is one week behind on the steel frame because of a delayed delivery of roof purlins. Roofing will start in week 19 instead of week 18. The completion date is not affected because the MEP rough-in can run in parallel with roofing.

Figure 1. Updated programme. Dashed line marks this week.

# 2. Health and safety

No reportable incidents since the last meeting (126 days).

Edge protection to be inspected after the roofing crew starts.

New starters must attend the induction before going on the roof.

# 3. Design questions

| RFI | Subject | Status | Owner |
| --- | --- | --- | --- |
| 012 | Reading room column grid at line C | Closed | Structural |
| 013 | Rooflight upstand height | Answered, see sketch SK-07 | Architect |
| 014 | Luminaire clash with supply duct, corridor 2 | Open | Services |
| 015 | Floor finish in children's area | Open | Architect |

# 4. Actions

| No. | Action | By | Due |
| --- | --- | --- | --- |
| 18.1 | Issue revised steel delivery date in writing | Contractor | Week 19 |
| 18.2 | Answer RFI 014 with revised ceiling height | Services engineer | Week 19 |
| 18.3 | Confirm floor finish sample for RFI 015 | Architect | Week 20 |
| 18.4 | Arrange roof edge protection inspection | Site manager | Week 19 |
| 18.5 | Circulate commissioning plan draft | Services engineer | Week 22 |

# 5. Next meeting

Week 19, same time, in the site office. Site walk of the roof level after the meeting; bring hard hats, harnesses not required (edge protection in place).