## Slide 1
North Wing Renovation
Project update for the school board
Programme, budget and next steps

## Slide 2
Project at a glance
2
Item | Status
Scope | Two-storey classroom wing, 16 classrooms, new entrance
Gross area | 2,950 m2
Contract sum | $7.9 million
Programme | 35 weeks, now at week 18
Completion | Before the start of the autumn term

## Slide 3
Programme
3

## Slide 4
Budget by package ($ thousands)
4
Chart: 
| Substructure | Frame | Roof | Envelope | MEP | Finishes | External works
Budget | 620 | 1450 | 540 | 1280 | 2100 | 1150 | 420
Forecast | 655 | 1520 | 560 | 1240 | 2140 | 1110 | 410

## Slide 5
Risks
5
Risk | Impact | Response
Late roof purlins | One week on roofing | Run MEP rough-in in parallel
Asbestos in existing ceiling voids | Cost and delay | Survey complete; removal booked for holidays
Wet weather | Envelope delay | Temporary roof cover over stair core
Long lead switchboards | Commissioning delay | Ordered in week 6, delivery confirmed week 26

## Slide 6
Next steps
6
• Roofing starts week 19
• Window installation from week 22
• Classroom finishes sample room ready for review in week 24
• Next board update in six weeks